## Sheet1
NEW MODEL TOOLING RELEASE PROCESS
PRE-GO | GO 1-1 | GO 1-2 | GO 2-1 | GO 2-2 | GO 2-3 / 2-4
This is the initial stage in the Tool Release Process. Pre-Go services as the Formal Business Award Notification. The Pre-Go authorizes the supper to: | This is the 2nd stage in Tool Release Process. Go-1 authorizes the supplier to: | This stage may follow Go 1-1 if the lead-time to procure tooling raw materials is excessively long. G0 1-2 authorizes the supplier to: | This stage may follow Go-1 if it is determined to be a requirement or necessity. Go 2-1 authorizes the supplier to build a prototype tool if: | This stage in the Tool Release Process authorizes the supplier to: | Either of these authorizations may be utilized if there is the need to release equipment, jigs, and fixtures apart from tooling due to differing lead-time requirements.
*Investigate tooling source ( l.e. SJ,SC, etc) | *Design tooling -Tool drawing -Cutter path development | *Purchase the necessary raw material only. An accompanying "Condition or tool release form" will define any tooling fabrication activity that has been authorized to begin. | *It is a requirement for design qualification as specified on the drawings. | *Begin mass production tooling build
*Determine requirements to meet total Lead-time based on the project schedule. | *Design Equipment |  | *It is a necessity to provide parts for a given production event (mass production tool with handwork is not acceptable/available) | *This stage may also authorize the supplier to begin production of check fixtures, jigs, and equipment (if not authorize separately)
*Select tool shop. Determine Catia capability. *Develop critical path for - Tooling - Equipment - Plant modifications | *Reserve tool shop time (based on Pre-go investigation and feedback to HAM-PH)
*Determine Tool material Lead-time | *Issue detailed tool quote
*Capacity Investigation -Tool & Equipment cycle time | *Issue detailed piece price using CCF (Cost Comparison Form)
*2nd tier Supplier selection * schedule -Includes outsourced parts & processes | *Issue detailed tool schedule
*Confirm completion of New Project Team authorization. | *Issue detailed equipment quote
*Continue specification maturation to countermeasure part manufacturability issues. | *Model build if applicable model requirements are: 1) noted on drawing and/or 2) are part of a suppliers' normal development activity